## Test Report
Test Case Report
Project Name | HAEFA Electronic Medical Record System Application
Client Name | Health and Education for All (HAEFA) |  |  |  |  | Pass | #REF!
Modul name | Frontend and Functional Testing |  |  |  |  | Fail | #REF!
Prepared by | Mustafa Tanim |  |  |  |  | Not Executed | #REF!
Reviewed by | Rashed Zahan |  |  |  |  | Out od Scope | #REF!
Project start date | Sep 26th, 2023
project end date | Oct 23rd, 2023
Version no | V 1.0
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out of Scope | Total Test Case
Login Functionality | 0 | 0 | 15 | 0 | 15
HomePage | 7 | 0 | 0 | 0 | 7
Patient Registration | 0 | 0 | 15 | 0 | 15
Doctor's Logout | 0 | 0 | 10 | 0 | 10
Doctor's Profile | #REF! | #REF! | #REF! | #REF! | #REF!
Patient Search | 13 | 3 | 0 | 0 | 16
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
0
0
Grand Total | #REF! | #REF! | #REF! | #REF! | #REF!

## Test Scenario
Project Name | HAEFA Electronic Medical Record System Application
Client Name | Health and Education for All (HAEFA)
Reference Document | SRS
Domain | Local Server/App
Created by | Rashed Zahan
Execution by | Mustafa Tanim & Rashed Zahan
Creation Date | Sep 26th, 2023
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
(TS_001) Login Functionality | SRS | Validate the working of "Login" functionality | P0
(TS_002) Dashboard/Home Page Functionality | SRS | Validate the "Dashboard or Home" page functionality | P0
(TS_003) Menu Functionality | SRS | Validate the working of "Menu" functionality and UI | P0
(TS_004) Logout Functionality | SRS | Validate the working of "Logout" functionality | P0
(TS_005) Patient Functionality | SRS | Validate the "Patient" page section functionality | P1
(TS_006) Reference Functionality | SRS | Validate the "Reference" page functionality | P1
(TS_007) Barcode Functionality | SRS | Validate the "Barcode" page functionality | P1
(TS_008) Report Functionality | SRS | Validate the "Report" section functionality | P1
(TS_009) Data Sync Functionality | SRS | Validate the "Data Sync" functionality under "Access Control" section | P1
(TS_010) User Functionality | SRS | Validate the "User" functionality under "Access Control" section | P1
(TS_011) Station 4B Functionality | SRS | Validate the "Role" functionality under "Access Control" section | P1
(TS_012) Station 4C Functionality | SRS | Validate the "Station" functionality under "Access Control" section | P1
(TS_013) Station 4D Functionality | SRS | Validate the "Setting" functionality under "System" section | P1
(TS_014) Station 4E Functionality | SRS |  | P1
(TS_015) Prescription Page | SRS |  | P1
(TS_016) Database testing

## Database testing
Database Test Report
PASS | 42
FAIL | 6
Not Executed | 8
Out of Scope | 0
Total | 56
Test Id | Test Scenario | Test Case Title | Pre-Requisites | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Tested by | Remarks/Screenshot | Dev. Status | Dev. Remarks | Regression Testing | Remarks(Testing)
TC_001 | TS_000 Database (Station-4A) | Validate "chief complaints" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | MDataPatientCCDetails ->Anxiety,Month,20,test300,Continuous | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_002 | TS_000 Database (Station-4A) | Validate "chief complaints" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_003 | TS_000 Database (Station-4A) | Validate "H/O present illness" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. All data insert into database except otherillness. |  | FAIL
TC_004 | TS_000 Database (Station-4A) | Validate "H/O present illness" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_005 | TS_000 Database (Station-4A) | Validate "H/O past illness" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. All data insert into database except otherillness. |  | FAIL
TC_006 | TS_000 Database (Station-4A) | Validate "H/O past illness" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_007 | TS_000 Database (Station-4A) | Validate "Family History" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. All data insert into database except otherillness. |  | FAIL
TC_008 | TS_000 Database (Station-4A) | Validate "Family History" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_009 | TS_000 Database (Station-4A) | Validate "Social History" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. "Social History" all data is failed to insert into database. 2. 'Housing Mediation' and 'Drinking water source' data insert into database in a same column. 3. 'SocialBehaviourId' isn't changing in database. |  | FAIL
TC_010 | TS_000 Database (Station-4A) | Validate "Social History" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_011 | TS_000 Database (Station-4A) | Validate "TB Screening" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link |  | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | Not Executed
TC_012 | TS_000 Database (Station-4A) | Validate "TB Screening" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link |  | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | Not Executed
TC_013 | TS_000 Database (Station-4A) | Validate "General Examination" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Anemia:++ Jaundice:++ Cyanosis:++ Edema:++ | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_014 | TS_000 Database (Station-4A) | Validate "General Examination" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_015 | TS_000 Database (Station-4A) | Validate "Systemic Examination" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Abdominal test32 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_016 | TS_000 Database (Station-4A) | Validate "Systemic Examination" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link |  | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | Not Executed
TC_017 | TS_000 Database (Station-4A) | Validate "Current Medication Taken" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Lomefloxacin 400 mg Tablet Duration: 6day Dose: 600mg Frequency:1+1+1+1+1+1 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_018 | TS_000 Database (Station-4A) | Validate "Current Medication Taken" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_019 | TS_000 Database (Station-4A) | Validate "Patient Mental Health" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_020 | TS_000 Database (Station-4A) | Validate "Patient Mental Health" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_021 | TS_000 Database (Station-4A) | Validate "Child Vaccination" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_022 | TS_000 Database (Station-4A) | Validate "Child Vaccination" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_023 | TS_000 Database (Station-4A) | Validate "Adult Vaccination" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_024 | TS_000 Database (Station-4A) | Validate "Adult Vaccination" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Para" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | 1 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Still Birth" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | 1 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Miscarriage" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | 0 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "MR" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | 1 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Live Male Birth" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | 1 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Live Female Birth" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | 1 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Child Mortality" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Male: 0-1 years Female: Below 5 years | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Pregnant" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NO | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "LMP" of calender data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | 2023-10-31 | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Contraception Method" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | IUD | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_002 | TS_000 Database (Station-4B) | Validate "Contraception Method" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Comments" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "What Product You Use During Menstruation?" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Sanitary Pad | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_002 | TS_000 Database (Station-4B) | Validate "What Product You Use During Menstruation?" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "How Often Do You Change / Replace?" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Twice Daily | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | PASS
TC_002 | TS_000 Database (Station-4B) | Validate "How Often Do You Change / Replace?" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_001 | TS_000 Database (Station-4B) | Validate "Cervical Cancer Screening" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link |  | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | Not Executed
TC_002 | TS_000 Database (Station-4B) | Validate "Cervical Cancer Screening" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link |  | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | Not Executed
TC_001 | TS_000 Database (Station-4B) | Validate "Where?" data insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link |  | 1. The Data should be inserted into the database | 1. The Data is inserted into the database. |  | Not Executed
TC_002 | TS_000 Database (Station-4B) | Validate "Where?" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link |  | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | Not Executed
TC_001 | TS_015 Database (Station-4C) | Validate the input data of "Provisional Diagnosis" section is insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Code/Common terms: Pain in right hip Disease: test25 | 1. The input data should insert into database | 1. The input data is inserted into database |  | PASS
TC_002 | TS_015 Database (Station-4C) | Validate "Provisional Diagnosis" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_002 | TS_015 Database (Station-4C) | Validate to display the "Search" suggestion result functionality | 1. The application should perfetly deploy in the server 2. Get the application link |  |  |  |  | Not Executed
TC_001 | TS_015 Database (Station-4C) | Validate the input data of "Lab Investigation" section is insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Search: X-Ray4(positive) Comments: test40 | 1. The input data should insert into database | 1. The input data is inserted into database |  | FAIL |  | Issue:Only "comment" doesn't inserted into the database
TC_002 | TS_015 Database (Station-4C) | Validate "Lab Investigation" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_001 | TS_015 Database (Station-4C) | Validate the input data of "Treatment Suggestion" section is insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Drug:Lomefloxacin 400 mg Tablet Frequency:1+1+1+1 Dose: 400mg Duration:10days Instruction:খাওয়ার ৩০ মিনিট আগে | 1. The input data should insert into database | 1. The input data is inserted into database |  | PASS
TC_002 | TS_015 Database (Station-4C) | Validate "Treatment Suggestion" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_001 | TS_015 Database (Station-4C) | Validate the input data of "Follow up Advice" section is insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Date:10/31/2023 Stutus:Good Comment:test34 | 1. The input data should insert into database | 1. The input data is inserted into database |  | PASS
TC_001 | TS_015 Database (Station-4C) | Validate the input data of "Advice" section is insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | AdviceID:ধুমপান ত্যাগ কর Advice:General Health Advice Add Advice: test500 | 1. The input data should insert into database | 1. The input data is inserted into database |  | PASS
TC_001 | TS_015 Database (Station-4C) | Validate the input data of "Refferal Section" section is insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Refferal: AN Health Center:Moheskhali Upazila Health Complex Status:test600 | 1. The input data should insert into database | 1. The input data is inserted into database |  | FAIL |  | Issue:Only "Status" doesn't inserted into the database
TC_002 | TS_015 Database (Station-4C) | Validate "Refferal Section" data display from database | 1. The application should perfetly deploy in the server 2. Get the application link | NA | 1. The Data should be displayed into the database | 1. The Data is displayed into the database |  | PASS
TC_001 | TS_015 Database (Station-4D/Station-4E) | Validate the input data of "CRA" section is insert into the database | 1. The application should perfetly deploy in the server 2. Get the application link | Age:50 Sex:Male BMI:20-24 kg/m2 CigerrateSmoker: No Systolic Blood Pressure:120 On Blood Pressure Medication: yes Diabetese:Absent | 1. The input data should insert into database | 1. The input data is inserted into database |  | PASS

## LogIn
Doctor's Login Test Report
PASS | 0
FAIL | 0
Not Executed | 15
Out of Scope | 0
Total | 15
Test Case Id | Test Scenario | Test Case Title | Pre-Requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Tested by | Remarks/Screenshot | Dev. Status | Dev. Remarks | Regression Testing | Remarks(Testing)
Scenarios>>
TC_001 | TS_001 (LogIn Functionality) | Validate logging into the Application using valid credentials | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-"admin@mail.com" Password-Admin@100% | 1. The web application should display on the browser properly. 2. After using valid credentials, the application should login. | 1. The web application is displayed on the browser properly. 2. After using valid credentials, the application is logged in. |  | Not Executed | Mustafa Tanim | NA
TC_002 | TS_001 (LogIn Functionality) | Validate logging into the Application using invalid credentials (i.e. Invalid email address and Invalid Password) | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-"admin223@mail.com" Password-Admin@1000% | 1. The web application should display on the browser properly. 2. After using invalid credentials, the application should not login. | 1. The web application is displayed on the browser properly. 2. After using invalid credentials, the application is not login. |  | Not Executed | Mustafa Tanim | NA
TC_003 | TS_001 (LogIn Functionality) | Validate logging into the Application using invalid email address and valid Password | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-"admin223@mail.com" Password-Admin@100% | 1. The web application should display on the browser properly. 2. After using invalid email and valid password, the application should not login. 3. The application should display an error message with proper context | 1. The web application is displayed on the browser properly. 2. After using invalid email and valid password, the application is not login. 3. The application is not displayed an error message with proper context |  | Not Executed | Mustafa Tanim | Issue: Valid message should be displayed
TC_004 | TS_001 (LogIn Functionality) | Validate logging into the Application using valid email address and invalid Password | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-"admin@mail.com" Password-Admin@10000% | 1. The web application should display on the browser properly. 2. After using valid email and invalid password, the application should not login. 3. The application should display an error message with proper context | 1. The web application is displayed on the browser properly. 2. After using valid email and invalid password, the application is not login. 3. The application is not displayed an error message with proper context |  | Not Executed | Mustafa Tanim | Issue: Valid message should be displayed
TC_005 | TS_001 (LogIn Functionality) | Validate logging into the Application without providing any credentials | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-null Password-null | 1. The web application should display on the browser properly. 2. Without providing any credentials, the application should not login. | 1. The web application is displayed on the browser properly. 2. Without providing any credentials, the application is not login. |  | Not Executed | Mustafa Tanim | NA
TC_006 | TS_001 (LogIn Functionality) | Validate logging into the Application using Keyboard keys (Tab and Enter) | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | NA | 1. The web application should display on the browser properly. 2. The keyboard keys should work properly for LogIn | 1. The web application is displayed on the browser properly. 2. The keyboard keys is working properly for LogIn |  | Not Executed | Mustafa Tanim | NA
TC_007 | TS_001 (LogIn Functionality) | Validate E-Mail Address and Password text field in the login page have the placeholder text | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | NA | 1. The web application should display on the browser properly. 2. E-Mail Address and Password text field in the login page should have the placeholder text | 1. The web application is displayed on the browser properly. 2. E-Mail Address and Password text field in the login page have placeholder text |  | Not Executed | Mustafa Tanim | NA
TC_008 | TS_001 (LogIn Functionality) | Validate Logging into the Application and browsing back using Browser back button | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | NA | 1. The web application should display on the browser properly. 2. After logging into the Application, browser back button should not work to go login page | 1. The web application is displayed on the browser properly. 2. After logging into the Application, browser back button is not working to go login page |  | Not Executed | Mustafa Tanim | NA
TC_009 | TS_001 (LogIn Functionality) | Validate Loggingout from the Application and browsing back using Browser back button | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | NA | 1. The web application should display on the browser properly. 2. After loggingout the Application, browser back button should not take to the "Dashboard" page | 1. The web application is displayed on the browser properly. 2. After loggingout the Application, browser back button is not taking to the "Dashboard" page |  | Not Executed | Mustafa Tanim | NA
TC_010 | TS_001 (LogIn Functionality) | Validate the text into the Password field is toggled to hide its visibility | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-"admin@mail.com" Password-Admin@100% | 1. The web application should display on the browser properly. 2. Password field should be toggled to hide its visibility | 1. The web application is displayed on the browser properly. 2. Password field is toggled to hide its visibility |  | Not Executed | Mustafa Tanim | NA
TC_011 | TS_001 (LogIn Functionality) | Validate the copying of the text into the Password field | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-"admin@mail.com" Password-Admin@100% | 1. The web application should display on the browser properly. 2. Password should not copying into the password field | 1. The web application is displayed on the browser properly. 2. Password is not able to copy into the password field |  | Not Executed | Mustafa Tanim | NA
TC_012 | TS_001 (LogIn Functionality) | Validate Logging into the Application, closing the Browser without loggingout and opening the application in the Browser again | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Email-"admin@mail.com" Password-Admin@100% | 1. The web application should display on the browser properly. 2. Even if close the browser while logged in, the application should be opened again | 1. The web application is displayed on the browser properly. 2. Even if close the browser while logged in, the application is opened again |  | Not Executed | Mustafa Tanim | NA
TC_013 | TS_001 (LogIn Functionality) | Validate the timeout functionality in the Login Session | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | NA | 1. The web application should display on the browser properly. 2. The application should not be timeout also logged in on time | 1. The web application should display on the browser properly. 2. The application logged in on time and didn't face any timeout session |  | Not Executed | Mustafa Tanim | NA
TC_014 | TS_001 (LogIn Functionality) | Validate the UI of the Login page | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | NA | 1. The web application should display on the browser properly. 2. The UI design should not be overlapped with any other elements and should not go out of the screen. | 1. The web application is displayed on the browser properly. 2. The UI design is not overlapping with any other elements and the element is not go out of the screen. |  | Not Executed | Mustafa Tanim | NA
TC_015 | TS_001 (LogIn Functionality) | Validate the Login page functionality in all the supported environments | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url "http://10.10.20.25:3002/login" into url section 3. Press Enter button or search this url (ER 01) 4. Click the ""LogIn"" button after giving the valid credentials (ER 02)" | Google Chrome, Mozilla Firefox, Microsoft Edge, | 1. The web application should display on the browser properly. 2. The application should display properly in all environments. | 1. The web application is displayed on the browser. 2. The application is displayed properly in all environment. |  | Not Executed | Mustafa Tanim | NA

## DashboardHome Page
HomePage Test Report
PASS | 7
FAIL | 0
Not Executed | 0
Out of Scope | 0
Total | 7
Test Case Id | Test Scenario | Test Case Title | Pre-Requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Tested by | Remarks/Screenshot | Dev. Status | Dev. Remarks | Regression testing | Tested by
Scenarios>>
TC_001 | TS_002 (Home Page) | Validate the text spelling accurecy in the home page | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button 5. Check the "Home Page" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The home page text should not be misspelled in the application | 1. The web application is displayed on the browser properly. 2. The home page text is not misspelled |  | PASS | Mustafa Tanim | NA
TC_002 | TS_002 (Home Page) | Validate the hover effect functionality in the application | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button 5. Check the "Home Page" (ER 02) | NA | 1. The web application should display on the browser properly. 2. Hover effect should work properly. | 1. The web application is displayed on the browser properly. 2. Hover effect is working properly. |  | PASS | Mustafa Tanim | NA
TC_003 | TS_002 (Home Page) | Validate the every clickable station is working properly | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button 5. Click every station of "Home Page" (ER 02) | NA | 1. The web application should display on the browser properly. 2. Every clickable station should be working properly. | 1. The web application is displayed on the browser properly. 2. Every clickable station is working properly. |  | PASS | Mustafa Tanim | NA
TC_004 | TS_002 (Home Page) | Validate the 'Home' button functionality under the bottom section in the application | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button 5. Click the 'Home' button (ER 02) | NA | 1. The web application should display on the browser properly. 2. 'Home' button should work properly and should be taken to the home page | 1. The web application is displayed on the browser properly. 2. 'Home' button is working properly and its taken to the home page |  | PASS | Mustafa Tanim | NA
TC_005 | TS_002 (Home Page) | Validate 'Profile' button functionality under the bottom section in the application | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button 5. Click the 'Profile' button (ER 02) | NA | 1. The web application should display on the browser properly. 2. 'Profile' button should display profile name, designation and logout button. | 1. The web application is displayed on the browser properly. 2. 'Profile' button is working properly and displayed the profile name, designation and logout button. |  | PASS | Mustafa Tanim | NA
TC_006 | TS_002 (Home Page) | Validate the UI design of Home page | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button 5. Check the "Home Page" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The UI design should not overlap with any other elements and should not go out of the screen. | 1. The web application is displayed on the browser properly. 2. The UI design is not overlapping with any other elements and not to go out of the screen. |  | PASS | Mustafa Tanim | NA
TC_007 | TS_002 (Home Page) | Validate the Home page functionality in all the supported environments | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button 5. Check the "Home Page" (ER 02) | Google Chrome, Mozilla Firefox, Microsoft Edge, | 1. The web application should display on the browser properly. 2. The application should display properly in all environments. | 1. The web application is displayed on the browser. 2. This link is working properly in all environment . |  | PASS | Mustafa Tanim | NA

## Smoke Test (hidden)
Smoke Test Report
PASS | 10
FAIL | 5
Not Executed | 0
Out of Scope | 4
Total | 19
Test Id | Functionality | Smoke Test | Test data | Actual Result | Result | Remarks
| Home page | Home page functionality | NA | Working fine | PASS | NA
TC_001 | Signup | Registration functionality | Name: Rashed E-mail: r.rashedzahan@gmail.com Pass: 123456 Con. Pass: 123456 | Successfully register | PASS | NA
TC_002 | SignIn | Login functionality | E-mail: r.rashedzahan@gmail.com Pass: 123456 | Successfully signin | PASS | NA
TC_003 | Logout | Logout functionality | NA | Successfully logout | PASS | NA
TC_004 | "Forgot Password" | Forgot password functionality | NA | Not found 'forgot password' function | Out of Scope | NA
TC_005 | "Remember me" buttom | Remember me button functionality | NA | Not working | FAIL | NA
TC_006 | Search item | Search item functionality | Biscuit, Noodles | Working fine | PASS | NA
TC_007 | "Cart" button | Add item to cart functionality | NA | Working but not merge | PASS | NA
TC_008 | "Buy Now" button | "Buy now" button functionality | NA | Working fine | PASS | NA
TC_009 | Change item in cart | Change item in cart functionality | NA | Working fine | PASS | NA
TC_010 | Payment | Payment functionality | NA | Not working | FAIL | Under development
TC_011 | Wishlist | Wishlist functionality | NA | Working fine | PASS | NA
TC_012 | My Order Section | My order functionality | NA | Data showing successfully | PASS | NA
TC_013 | Invoice | Invoice functionality | NA | Not working | FAIL | Under development
TC_014 | Place order | Place order functionality | NA | Working but not functional | PASS | NA
TC_015 | Track order | Track order functionality | NA | NA | Out of Scope | Not found
TC_016 | Cancel order | Cancel order functionality | NA | NA | Out of Scope | Not found
TC_017 | Return item | Return item functionality | NA | NA | Out of Scope | Not found
TC_018 | Rate item | Rate item functionality | NA | Functional issue | FAIL | NA
TC_019 | Review item | Review item functionality | NA | Functional issue | FAIL | NA

## Menu
Patient Registration Test Report
PASS | 2
FAIL | 1
Not Executed | 41
Out of Scope | 0
Total | 44
Test Case Id | Test Scenario | Test Case Title | Pre-Requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Tested by | Remarks/Screenshot | Dev. Status | Dev. Remarks | Regression Testing | Remarks(Testing)
Scenarios>>
TC_001 | TS_003 (Menu) | Validate the page header in the "Patient Registration" page | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. Page heading of "Dashboard" should display on the screen | 1. The web application is displayed on the browser properly. 2. Page heading of "Dashboard" is displayed on the screen |  | Not Executed | Mustafa Tanim | NA
TC_002 | TS_003 (Menu) | Validate the page title in the "Patient Registration" page | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. Page title of "Patient Registration" should display on the screen | 1. The web application is displayed on the browser properly. 2. Page title of "Patient Registration" is displayed on the screen |  | Not Executed | Mustafa Tanim | NA
TC_003 | TS_003 (Menu) | Validate the page url in the "Patient Registration" page | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. Page url of "Patient Registration" should display on the screen | 1. The web application is displayed on the browser properly. 2. Page url of "Patient Registration" is displayed on the screen |  | Not Executed | Mustafa Tanim | NA
TC_004 | TS_003 (Menu) | Validate the all buttons functionality | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The text alignment of "Patient Registration" should same on the screen | 1. The web application should display on the browser properly. 2. The text alignment of "Patient Registration" is same on the screen |  | Not Executed | Mustafa Tanim | NA
TC_005 | TS_003 (Menu) | Validate the application logo functionality | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. Copy-paste functionality should work properly in text field | 1. The web application should display on the browser properly. 2. Copy-paste functionality is working properly in text field |  | Not Executed | Mustafa Tanim | NA
TC_006 | TS_003 (Menu) | Validate the application "Menu" toggle button functionality | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should able to delete by pressing the backspace key on the keyboard. | 1. The web application is displayed on the browser properly. 2. The user is able to delete by pressing the backspace key on the keyboard. |  | Not Executed | Mustafa Tanim | NA
TC_007 | TS_003 (Menu) | Validate the application menu item functionality | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. There should have placeholder in every text field | 1. The web application is displayed on the browser properly. 2. There have placeholder in every text field |  | Not Executed | Mustafa Tanim | NA
TC_008 | TS_003 (Menu) | Validate the application sub-menu item functionality | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should not able to save the details without entering data on mandatory fields. | 1. The web application is displayed on the browser properly. 2. The user is not able to save the details without entering data on mandatory fields. |  | Not Executed | Mustafa Tanim | NA
TC_009 | TS_003 (Menu) | Validate the application menu item hover effect | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should able to save the details with entering data on mandatory fields. | 1. The web application is displayed on the browser properly. 2. The user is not able to save the details with entering data on mandatory fields. |  | Not Executed | Issue: some mandatory field may be not mentioned | TC_009
TC_010 | TS_003 (Menu) | Validate the application sub-menu item hover effect | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The alert message should shows when the user save data without the mandatory field | 1. The web application is displayed on the browser properly. 2. The alert message had shown when the user save data without the mandatory field |  | Not Executed | Mustafa Tanim | NA
TC_011 | TS_003 (Menu) | Validate the application all menu item icon functionality. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The mandatory fields of the application should be marked with a special character like a red star icon (*). | 1. The web application is displayed on the browser properly. 2. The mandatory fields of the application has marked with a special character like a red star icon (*). |  | Not Executed | Mustafa Tanim | NA
TC_012 | TS_003 (Menu) | Validate that the dropdown field is clickable or not | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The dropdown field should be clickable. | 1. The web application is displayed on the browser properly. 2. The dropdown field is clickable. |  | Not Executed | Mustafa Tanim | NA
TC_013 | TS_003 (Menu) | Validate that when Clicking on the dropdown list (value of dropdown) showing or not. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. After clicking on the dropdown list, the value should show. | 1. The web application is displayed on the browser properly. 2. After clicking on the dropdown list, the value is showed. |  | Not Executed | Mustafa Tanim | NA
TC_014 | TS_003 (Menu) | Validate that the dropdown can be scrolled down by clicking the down arrow | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The dropdown should be scrolled down by clicking the down arrow | 1. The web application is displayed on the browser properly. 2. The dropdown can be scrolled down by clicking the down arrow |  | Not Executed | Mustafa Tanim | NA
TC_015 | TS_003 (Menu) | Validate that the user is able to select the dropdown by the "tab" key from the keyboard. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should be able to select the dropdown by the "tab" key from the keyboard. | 1. The web application is displayed on the browser properly. 2. The user is able to select the dropdown by the "tab" key from the keyboard. |  | Not Executed | Mustafa Tanim | NA
TC_016 | TS_003 (Menu) | Validate the title of all menu item | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The upazila dropdown list should not show without selecting a district. | 1. The web application is displayed on the browser properly. 2. The upazila dropdown list can not show without selecting a district. |  | Not Executed | Mustafa Tanim | NA
TC_017 | TS_003 (Menu) | Validate the title of all sub-menu item | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The union dropdown list should not show without selecting a upazila. | 1. The web application is displayed on the browser properly. 2. The union dropdown list can not show without selecting a upazila . |  | Not Executed | Mustafa Tanim | NA
TC_018 | TS_003 (Menu) | Validate the dynamic of menu bar | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The radio buttons should be selectable. | 1. The web application is displayed on the browser properly. 2. The radio buttons are selectable. |  | Not Executed | Mustafa Tanim | NA
TC_019 | TS_003 (Menu) | Validate the scroll bar of menu bar option | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The radio buttons should be clickable by using the tab on the keyboard | 1. The web application is displayed on the browser properly. 2. The radio buttons are clickable by using the tab on the keyboard |  | Not Executed | Mustafa Tanim | NA
TC_020 | TS_003 (Menu) | Validate the responsiveness of menu bar option | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should not select multiple radio buttons | 1. The web application is displayed on the browser properly. 2. The user can't select multiple radio buttons |  | Not Executed | Mustafa Tanim | NA
TC_021 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The alignment of the radio button should same in all browsers. | 1. The web application is displayed on the browser properly. 2. The alignment of the radio button is same in all browsers. |  | Not Executed | Mustafa Tanim | NA
TC_022 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The date of birth field's calender should be enabled. | 1. The web application is displayed on the browser properly. 2. The date of birth field's calender is enabled. |  | Not Executed | Mustafa Tanim | NA
TC_023 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should be able to click on the date field | 1. The web application is displayed on the browser properly. 2. The user is able to click on the date field |  | Not Executed | Mustafa Tanim | NA
TC_024 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Check the"Menu bar" option from left side of application (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should be able to change and selected (date picker functionality) the date accordingly | 1. The web application is displayed on the browser properly. 2. The user is able to change and selected (date picker functionality) the date accordingly |  | Not Executed | Mustafa Tanim | NA
TC_025 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The month and day should accept two digits in the 'DOB' | 1. The web application is displayed on the browser properly. 2. The month and day can accept two digits in the 'DOB' |  | Not Executed | Mustafa Tanim | NA
TC_026 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The year should accepts four digits in the 'DOB'. | 1. The web application is displayed on the browser properly. 2. The year can accepts four digits in the 'DOB'. |  | Not Executed | Mustafa Tanim | NA
TC_027 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The input field should not accept special characters in the 'DOB'. | 1. The web application is displayed on the browser properly. 2. The input field is not accept special characters in the 'DOB'. |  | Not Executed | Mustafa Tanim | NA
TC_028 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The leap year dates should be accepted in the 'DOB'. | 1. The web application is displayed on the browser properly. 2. The leap year dates can be accepted in the 'DOB'. |  | Not Executed | Mustafa Tanim | NA
TC_029 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The "Patient Age" should be calculated in years with "Date of birth" calendar | 1. The web application is displayed on the browser properly. 2. The "Patient Age" is calculated in years with "Date of birth" calendar |  | Not Executed | Mustafa Tanim | NA
TC_030 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The fixed section of "Registration Number" should be similar with "health code" from home page. | 1. The web application should display on the browser properly. 2. The "Registration Number" follows the requirements. |  | Not Executed | Mustafa Tanim | NA
TC_031 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The "contact number" field should not be entered in the special character | 1. The web application is displayed on the browser properly. 2. The "contact number" field is not entered in the special character |  | Not Executed | Mustafa Tanim | NA
TC_032 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The "contact number" field should not be accept the string value | 1. The web application is displayed on the browser properly. 2. The "contact number" field is not allow the string value, except this (e,E) character |  | Not Executed | Mustafa Tanim | NA
TC_033 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The user should be able to copy and paste the contact number in the field | 1. The web application is displayed on the browser properly. 2. The user is able to copy and paste the contact number in the field |  | Not Executed | Mustafa Tanim | NA
TC_034 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. There should have placeholder for the contact number text box | 1. The web application is displayed on the browser properly. 2. There have placeholder for the contact number text box |  | Not Executed | Mustafa Tanim | NA
TC_035 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. All districts name should be displayed under the "District" dropdown section | 1. The web application is displayed on the browser properly. 2. All districts name are displayed under the "District" dropdown section |  | Not Executed | Mustafa Tanim | NA
TC_036 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. All upazila names should be displayed with "District" name under the "Upazila" dropdown section | 1. The web application is displayed on the browser properly. 2. All upazila names are displayed with "District" name under the "Upazila" dropdown section |  | Not Executed | Mustafa Tanim | NA
TC_037 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. "Save & next" button should be clickable and should work properly | 1. The web application is displayed on the browser properly. 2. "Save & next" button is clickable and working properly |  | Not Executed | Mustafa Tanim | NA
TC_038 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. There should have hover effect of "Save & next" button | 1. The web application is displayed on the browser properly. 2. There have hover effect of "Save & next" button |  | Not Executed | Mustafa Tanim | NA
TC_039 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. After clicking on "Save & next" button without entering data in the mandatory field, there should be shown an error message for the mandatory field. | 1. The web application is displayed on the browser properly. 2. After clicking on "Save & next" button without entering data in the mandatory field, the error message displayed. Message: "Error. Registration Code or Number Format Invalid" |  | Not Executed | Mustafa Tanim | NA
TC_040 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. "Home" button should be clickable and should work properly | 1. The web application is display on the browser properly. 2. "Home" button is clickable and is working properly |  | Not Executed | Mustafa Tanim | NA
TC_041 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. "Profile" button should be clickable and should work properly | 1. The web application is display on the browser properly. 2. "Profile" button is clickable and is working properly |  | Not Executed | Mustafa Tanim | NA
TC_042 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | NA | 1. The web application should display on the browser properly. 2. The UI design should not overlap any other elements and not to go out of the screen. | 1. The web application is displayed on the browser properly. 2. The UI design is not overlapping any other elements and not to go out of the screen. |  | PASS | Mustafa Tanim | NA
TC_043 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) | Google Chrome, Mozilla Firefox, Microsoft Edge, | 1. The web application should display on the browser properly. 2. This link should work in all environments. | 1. The web application is displayed on the browser. 2. This link is working in all environment. |  | PASS | Mustafa Tanim | NA
TC_044 | TS_003 (Patient Registration) |  | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Home Page" 5. Click the "Patient Registration" (ER 02) |  | 1. The web application should display on the browser properly 2. The application should have the option to update/edit for a registered patient | 1. The web application is displayed on the browser 2. We didn't find any option to update/edit |  | FAIL | Mustafa Tanim | NA

## Logout
Doctor's Logout Test Report
PASS | 0
FAIL | 0
Not Executed | 10
Out of Scope | 0
Total | 10
Test Case Id | Test Scenario | Test Case Title | Pre-Requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Tested by | Remarks/Screenshot | Dev. Status | Dev. Remarks | Regression Testing | Remarks(Testing)
Scenarios>>
TC_001 | TS_004 (Logout Functionality) | Validate after successful login on the profile icon to check logout button is visible or not. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly. 2. After successful login from the profile icon, logout button should visible. | 1. The web application is displayed on the browser properly. 2. After successful login from the profile icon, logout button is visible. |  | Not Executed | Mustafa Tanim | NA
TC_002 | TS_004 (Doctor's Logout) | Validate Logging out by selecting Profile option from "Dashboard" | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly. 2. From "Profile" option, logout should work properly. | 1. The web application is displayed on the browser properly. 2. From "Profile" option, logout is working properly. |  | Not Executed | Mustafa Tanim | NA
TC_003 | TS_004 (Doctor's Logout) | Validate clicking on the logout button, after successful logout on the login screen press the back button. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly. 2. After successful logging out, back button should not work. | 1. The web application is displayed on the browser properly. 2. After successful logging out, back button is not work. |  | Not Executed | Mustafa Tanim | NA
TC_004 | TS_004 (Doctor's Logout) | Validate after logout, try to re-login with the same or different account it’s allowing or not | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly. 2. After logging out, re-login should work by same or different account. | 1. The web application is displayed on the browser properly. 2. After logging out, re-login is working properly by same or different account. |  | Not Executed | Mustafa Tanim | NA
TC_005 | TS_004 (Doctor's Logout) | Validate the spelling of the Logout option | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly. 2. The logout text should not be misspelled in the application | 1. The web application should display on the browser properly. 2. The logout text is not misspelled in the application |  | Not Executed | Mustafa Tanim | NA
TC_006 | TS_004 (Doctor's Logout) | Validate the logout button is clickable after user is logged in the account. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly. 2. The logout button should be clickable | 1. The web application is displayed on the browser properly. 2. The logout button is clickable |  | Not Executed | Mustafa Tanim | NA
TC_007 | TS_004 (Doctor's Logout) | Validate logout with valid user, close tab and re-open (Chrome browser ctrl+Shift+ t) check user is logged in or auto logout | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The website should display on the browser properly. 2. The application should be logged out 3. After logging out, the screen should dispaly LogIn page | 1. The website is displayed on the browser properly. 2. The application is logged out 3. After logging out, the screen is dispalyed LogIn page |  | Not Executed | Mustafa Tanim | NA
TC_008 | TS_004 (Doctor's Logout) | Validate the sign-off page redirect to the page where it allows login | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly 2. After loggingout the Application, "LogIn" page should display | 1. The web application is displayed on the browser properly. 2. After loggingout the Application, "LogIn" page is displayed |  | Not Executed | Mustafa Tanim | NA
TC_009 | TS_004 (Doctor's Logout) | Validate the UI of the Logout option. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | NA | 1. The web application should display on the browser properly. 2. The UI design should not overlap any other elements and not to go out of the screen. | 1. The web application is displayed on the browser properly. 2. The UI design is not overlapping any other elements and not to go out of the screen. |  | Not Executed | Mustafa Tanim | NA
TC_010 | TS_004 (Doctor's Logout) | Validate the Logout functionality in all the supported environments | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://10.10.20.25:3002/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button then go to "Dashboard" . 5. Click "Profile" button from right top section 5. Click the "Logout" button (ER 02) | Google Chrome, Mozilla Firefox, Microsoft Edge, | 1. The web application should display on the browser properly. 2. This link should work in all environments. | 1. The web application is displayed on the browser. 2. This link is working in all environment. |  | Not Executed | Mustafa Tanim | NA

## Profile
Patient Search Test Report
PASS | 13
FAIL | 3
Not Executed | 0
Out of Scope | 0
Total | 16
Test Case Id | Test Scenario | Test Case Title | Pre-Requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Tested by | Remarks/Screenshot | Dev. Status | Dev. Remarks | Regression Testing | Remarks(Testing)
Scenarios>>
TC_001 | TS_005 (Search) | Validate searching with an existing registered patient name/card/nid/mobile | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 Mobile- 0123456789 NAME-Rahim Ullah | 1. The web application should display on the browser properly. 2. By searching, the existing registered patient name/card/nid/mobile should display on the screen | 1. The web application is displayed on the browser properly. 2. By searching, the existing registered patient name/nid/mobile is displayed on the screen but card doesn't work |  | FAIL | Mustafa Tanim | NA
TC_002 | TS_005 (Search) | Validate searching with a non-existing registered patient name/card/nid/mobile | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 222456789 Mobile- 012340009 NAME-KarimUllah | 1. The web application should display on the browser properly. 2. Non-existing patient details should not displayed by serching. | 1. The web application is displayed on the browser properly. 2.Non-existing patient is not displayed by serching |  | PASS | Mustafa Tanim | NA
TC_003 | TS_005 (Search) | Validate searching without providing any patient name/card/nid/mobile | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NA | 1. The web application should display on the browser properly. 2. Search without a patient name/card/nid/mobile, the browser should show nothing | 1. The web application is displayed on the browser properly. 2. Search without a patient name/card/nid/mobile, the browser is showing nothing |  | PASS | Mustafa Tanim | NA
TC_004 | TS_005 (Search) | Validate searching for a patient name/card/nid/mobile after login to the Application | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NA | 1. The web application should display on the browser properly. 2. After logging to the application, the browser should display the patient by searching full name and half name. | 1. The web application should display on the browser properly. 2. After logging to the application, the browser is displayed the patient by searching with half name but not found with full name. |  | FAIL | Mustafa Tanim | Here, Data found with the single name. But the application didn't display any information if we search for full name.
TC_005 | TS_005 (Search) | Validate the Search functionality and Search page have text field placeholders | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NA | 1. The web application should display on the browser properly. 2. "Search" option should work properly and "Search" text field should have placeholder | 1. The web application is displayed on the browser properly. 2. "Search" option is working properly and "Search" text field have placeholder |  | PASS | Mustafa Tanim | NA
TC_006 | TS_005 (Search) | Validate Search using the patient name/card/nid/mobile from the patient description | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 Mobile- 0123456789 NAME-Rahim Ullah | 1. The web application should display on the browser properly. 2. Using patient name/card/nid/mobile to search should return the patient description | 1. The web application is displayed on the browser properly. 2. Name/NID/Mobile options are working properly, but Card option is not working. |  | FAIL | Mustafa Tanim | NA
TC_007 | TS_005 (Search) | Validate and observe how much time required for getting the search result. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 Mobile- 0123456789 NAME-Rahim Ullah | 1. The web application should display on the browser properly. 2. The application should display the result as soon as possible | 1. The web application should display on the browser properly. 2. The application is displayed the result within 1 sec. |  | PASS | Mustafa Tanim | Issue: Searching functionality process is slow as per UAT
TC_008 | TS_005 (Search) | Validate auto suggestion shown on adding a keyword or not. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 or, Mobile- 0123456789 or, NAME-Rahim | 1. The web application should display on the browser properly. 2. Auto suggestion should shown on adding a keyword | 1. The web application is displayed on the browser properly. 2. Auto suggestion has shown on adding a keyword |  | PASS | Mustafa Tanim | NA
TC_009 | TS_005 (Search) | Validate the NID search option is working properly | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) |  | 1. The web application should display on the browser properly. 2. When search with NID number, the application should search or check with NID number while register a new patient | 1. The web application is displayed on the browser. 2. While searching with NID number,The application is checking the search value from "NID", "Birth" and "ID No" from backend |  | FAIL | Mustafa Tanim | NA
TC_010 | TS_005 (Search) | Validate an warning message is displayed for blank input. | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- null or, Mobile-null or, NAME-null or, Card-null | 1. The web application should display on the browser properly. 2. An warning message should display for blank input in the search box. | 1. The web application is displayed on the browser properly. 2. An warning message is display for blank input in the search box. |  | PASS | Mustafa Tanim | NA
TC_011 | TS_005 (Search) | Validate if the user can paste the keyword with the mouse | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 or, Mobile- 0123456789 or, NAME-Rahim Ullah | 1. The web application should display on the browser properly. 2. The user should paste the keyword with the mouse | 1. The web application is displayed on the browser properly. 2. The user can paste the keyword with the mouse |  | PASS | Mustafa Tanim | NA
TC_012 | TS_005 (Search) | Validate the search button functionality by adding keyword in search text field | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 or, Mobile- 0123456789 or, NAME-Rahim Ullah | 1. The web application should display on the browser properly. 2. The user should add any registered keyword in the search option and it should work | 1. The web application is displayed on the browser properly. 2. The user can add any registered keyword in the search option and it will work |  | PASS | Mustafa Tanim | NA
TC_013 | TS_005 (Search) | Validate 'Search' textbox field and the button having search icon or text are displayed on all the station of the Application | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 or, Mobile- 0123456789 or, NAME-Rahim Ullah | 1. The web application should display on the browser properly. 2. In the search option, search icon or text should display on all the station of the Application | 1. The web application is displayed on the browser properly. 2. In the search option, search icon or text are displayed on all the station of the Application |  | PASS | Mustafa Tanim | NA
TC_014 | TS_005 (Search) | Validate we can use all the options of Search functionality using the Keybaord keys | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NID- 123456789 or, Mobile- 0123456789 or, NAME-Rahim Ullah | 1. The web application should display on the browser properly. 2. By using keyboard keys, the search option should work properly. | 1. The web application is displayed on the browser properly. 2. By using keyboard keys, the search option is working properly. |  | PASS | Mustafa Tanim | NA
TC_015 | TS_005 (Search) | Validate Page Heading, Page URL and Page Title of the 'Search' page | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NA | 1. The web application should display on the browser properly. 2. Page Heading, Page Title and Page URL of search option should display on the screen. | 1. The web application is displayed on the browser properly. 2. Page Heading, Page Title and Page URL of search option is displayed on the screen. |  | PASS | Mustafa Tanim | NA
TC_016 | TS_005 (Search) | Validate the UI of Search page and functionality in the application | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | NA | 1. The web application should display on the browser properly. 2. The UI design should not overlap any other elements and should not to go out of the screen. | 1. The web application is displayed on the browser properly. 2. The UI design is not overlapping any other elements and not to go out of the screen. |  | PASS | Mustafa Tanim | NA
TC_017 | TS_005 (Search) | Validate the Search functionality in all the supported environments | 1. Make sure the device has internet connection. 2. Confirm the application url | 1. Open the browser. 2. Write url ""http://localhost/"" into url section 3. Press Enter button or search this url (ER 01) 4. Click the "LogIn" button and then go to any station from "Home page". 5. Check "Search" option (ER 02) | Google Chrome, Mozilla Firefox, Microsoft Edge, | 1. The web application should display on the browser properly. 2. This "Search" option should work in all environments. | 1. The web application is displayed on the browser. 2. This "Search" option is working in all environment. |  | PASS | Mustafa Tanim | NA

## Bug Report (hidden)
Total Bug report:39
Bug Report |  | Bug Report |  | Bug Report
BR_001 | TC_002 (Home page) | BR_002 | TC_009 (Home page) | BR_003 | TC_010 (Home page)
Issue: | The web application title issue | Issue: | The hover effect of 'How to buy', 'B2B sales', 'Login' & 'Sign up' button on top section | Issue: | The UI design of header section
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Place the mouse on 'How to buy', 'B2B sales', 'Login' & 'Sign up' button from the right top section | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1giYcGr0EcLZHyd2CjsoJoRVEmY6maMGp/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1RonIi4QaWWxIIYe9MA58SFSAKfDOKIUg/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/15Vi1t8U6oflx-hl6z47RKg6cNVpscnJx/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_004 | TC_017 (Home page) | BR_005 | TC_023 (Home page) | BR_006 | TC_025 (Home page)
Issue: | The 'Cart' button shows hover-text or infotip GUI elements | Issue: | The page headline for every displayed page from menu option | Issue: | The dropdown list displayed when mouse place on 'About Us' button
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Place mouse on 'Cart' button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Place the mouse on the text in menu | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Place mouse on 'About Us' button from munu
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1xrPMq257EStypNrF-ehurDiwGALTXALa/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1ANYsBeWiIfU8AT337xXti1wBS80sahHk/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1SNOnccPrbm1jiAHWZNtW0Zj8c652UKVd/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_007 | TC_045 (Home page) | BR_008 | TC_052 (Home page) | BR_009 | TC_066 (Home page)
Issue: | The 'Add to Cart' button functionality in every slide elements under 'Chips' section | Issue: | The 'Add to Cart' button functionality in every slide elements under 'Biscuit & Bakery' section | Issue: | The 'Add to Cart' button functionality in every slide elements under 'Noodles' section
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to 'Chips' section 5. Click on 'Add to Cart' button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to 'Biscuit & Bakery' section 5. Click on 'Add to Cart' button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to 'Noodles' section 5. Click on 'Add to Cart' button
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1zzvdevknPNPZMHEZ4ADyU9iJIj13JlXi/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1F75ds112l3fdZ5cEw2XXfAm-v3ozLG62/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1g2nNsgccWCmrTWprEo2aGRTcaGJWPJ-F/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_010 | TC_073 (Home page) | BR_011 | TC_080 (Home page) | BR_012 | TC_092 (Home page)
Issue: | The 'Add to Cart' button functionality in every slide elements under 'Snacks' section | Issue: | The 'Add to Cart' button functionality in every slide elements under 'Home Care' section | Issue: | The social media icon functionality in the footer section
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to 'Snacks' section 5. Click on 'Add to Cart' button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to 'Home Care' section 5. Click on 'Add to Cart' button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to "Footer" 5. Click the all social media icon
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1brdHWjZB4tx3lLNunlCUhClRh4VJnuIi/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1CV_QYE9H4A79EWfyTcwi9eZEiqocIu3k/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1Ck3euw0fVYumMzOUWaVJiL2bWZ_AYiK8/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_013 | TC_095 (Home page) | BR_014 | TC_012 (Registration) | BR_015 | TC_006 (LogIn)
Issue: | The copyright section functionality | Issue: | All the fields in the Register Account page have the proper placeholders | Issue: | Forgot Password' link is available in the Login page and is working
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to "Footer" 5. Check the copyright section | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "Sign Up" button from right top section | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from right top section
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1rLXGg40ZfasVQBEwkFvFXCZXgiJwOCg_/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/14wxBhFgMYKVswhjQPxzRs9j_EkKdvZzR/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1eojFK5Ea0eduRJLZECYgsl6n4KVY2P6J/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_016 | TC_008 (LogIn) | BR_017 | TC_015 (LogIn) | BR_018 | TC_016 (LogIn)
Issue: | E-Mail Address and Password text field in the login page have the placeholder text | Issue: | The Password is not visible in the Page Source | Issue: | Logging into the Application after changing the password
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from right top section | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from right top section | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from right top section
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1J1A60H___bhm54eoAhY0fye2iWtOtcvv/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1b1K_I4vakGxX_hh6N9HC2ZB1naUH5XWa/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1xNr9LmCklMrbguQ4u84_eae8g0YQQG7a/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_019 | TC_019 (LogIn) | BR_020 | TC_006 (Account Information) | BR_021 | TC_008 (Account Information)
Issue: | Remember me' check box functionality | Issue: | 'TAB' and 'ENTER" keys are working properly in side MenuBar of 'My Account' page | Issue: | Making all the fields in the 'Change Password' option on 'My Account' page
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click on "LogIn" button from right top section | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from footer section 5. Check "My Account" page using TAB & Enter keys | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from footer section 5. Check the 'Change Password' option on "My Account" page
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1qxNxxOl2z_tTNcJuy99BXuNp0WWUqDk3/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/16PIUcrq8XoXzEujxgJ3RGJZOsoywDLN2/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1HByU0Rb1wJ3hY06mWUOOqN4O9IA8mREs/view?usp=sharing
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_022 | TC_015 (Account Information) | BR_023 | TC_021 (Account Information) | BR_024 | TC_023 (Account Information)
Issue: | Largest image file uploading for profile picture in "My Account" page | Issue: | The mandatory * red marked of "Address" textfields in 'My Account' page | Issue: | The logo, social medialink, payment information, copyright in the footer section
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from right-top section 5. Check "My Account" page | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from right-top section 5. Check "My Account" page and go to "Address" | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click the "LogIn" button from right-top section 5. Check "My Account" page and go to footer section
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/15qqtir1Beig180pUwwz8tu8mENIDiHHe/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1rcBX3watam8_877k0RrJ3VcMUZxSNsbv/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1Dy_yQTh3uUp0qDnAT3wpSm4TP4asCjvI/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_025 | TC_007 (View Item) | BR_0026 | TC_008 (View Item) | BR_027 | TC_019 (View Item)
Issue: | The User is able to write a review for the Product from the 'Customer Reviews' tab of Product Display Page | Issue: | The 'Reviews' tab when there are no reviews or zero reviews added | Issue: | Navigating to the Product Display page by using the Product Image in the 'Add to Cart' section
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "Search" option & Search any product 5. Click any product | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "Search" option & Search any product 5. Click any product | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click to "Add to Cart" button and choose any product
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1du72xwZUZhdd8M1lI3FML2zA8yphKXTB/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1MiEWS5oGaKx5CrQAKyVM2BIQAb38AyEk/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1y0VitgAU0ieqOPqVJsix19Z2_4bNXRTS/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_028 | TC_023 (View Item) | BR_029 | TC_002 (Add to cart) | BR_030 | TC_003 (Add to cart)
Issue: | The functionality of buttons and links on header, footer sections in the Product Display page | Issue: | Adding the product to Cart from 'Wish List' Page | Issue: | Adding the product to Cart by clicking "Buy Now" button from 'Wish List' Page
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "Search" option & Search any product 5. Click any product | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Check the "Wish List" page 6. Click the "Add to cart" button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Check the "Wish List" page 6. Click the "Buy Now" button
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1lnxGmzi5VOTHmKHLPbC47XNSNgRnuWF5/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/15ND8NaU8nRaSi3tYgoaEiblVcasmhsx9/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1oDW09dJ3idIi3KbCl4ifouD6DoSemKb-/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_031 | TC_003 (Wish List) | BR_032 | TC_002 (Change Password) | BR_033 | TC_005 (Change Password)
Issue: | Adding a product to 'Wish List' page from the Product display in the 'Combo Pack' section of 'Home' page | Issue: | Changing the password | Issue: | All the Password fields in the 'Change Password' page are marked as mandatory
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Scroll down to "Combo Pack" section 5. Click any "Combo Pack" from this section 6. Click any product & "wish list" button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Click the "Change Password" button from left side bar | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Click the "Change Password" button from left side bar
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/14TomMknq-OLUyUZHOQ-MYaznaQoPLjjW/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1_rh2mPXTkpdHDnfK3mED2dtsGCT7mOf5/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/15Vi1t8U6oflx-hl6z47RKg6cNVpscnJx/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_034 | TC_006 (Change Password) | BR_035 | TC_007 (Change Password) | BR_036 | TC_006 (Address)
Issue: | Back button in the 'Change Password' page | Issue: | Page Heading, Page Title and Page URL in the 'Change Password' page | Issue: | Back button in the 'Edit Address' page
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Click the "Change Password" button from left side bar 6. Click back button from the browser | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Click the "Change Password" button from left side bar | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Click the "Address" button from left side bar) 6. Press back button from "Edit Address" page
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/1wTjGWNutSZSHYJTnjUqUSnweOGoJrghZ/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1hdyJniGUwCfzO1dCJTnUnHtBAu1dNGGt/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1B7nVFU0p4AkNIbqZ-lYI06AlwRP7U3uz/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan
Bug Report |  | Bug Report |  | Bug Report
BR_037 | TC_007 (Address) | BR_038 | TC_002 (Buy Now) | BR_039 | TC_006 (Buy Now)
Issue: | Back button in the 'Address' page | Issue: | Adding the product to 'Checkout' page from 'Wish List' Page | Issue: | The "Buy Now" button is clickable from anywhere in the web application
Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Go to "My Account" button on the right-top section 5. Click the "Address" button from left side bar | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click "My Account" button on the right-top section 5. Click the "Wish List" button and chose any product 6. Click the "Buy Now" button | Reproducing steps | 1. Open the browser. 2. Write url "https://ifadeshop.com/" into url section 3. Press Enter button or search this url 4. Click any product from the web application 5. Click the "Buy Now" button
EVN: | Live server | EVN: | Live server | EVN: | Live server
Module | Functional & UI Design Testing | Module | Functional & UI Design Testing | Module | Functional & UI Design Testing
ScreenShot | https://drive.google.com/file/d/16OA0DTcZzDmL42znFLdYyX-tyjXyojZI/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1IaKIM5w8oDPa3kJxYmi_rmZmu5KK_p8m/view?usp=drive_link | ScreenShot | https://drive.google.com/file/d/1rBnOuzkDDbv6_YICCviidzDxKtaLxah2/view?usp=drive_link
Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan | Responsible QA: | Rashed Rahan